# RISK MANAGEMENT PLAN

## Booked Solid Inspector · Outcrop Holdings, Inc.

Version 1 · 9 August 2026

## How this is built

Every risk here is one this business actually carries. No generic categories. Where something has already happened, it says so — and those entries carry more weight than any estimate, because they're evidence rather than speculation.

Scoring is deliberately simple. Precise probability numbers on a pre-revenue business are false confidence.

| Likelihood | Meaning |
| --- | --- |
| High | Has happened, or will happen at 500 clients |
| Medium | Plausible within twelve months |
| Low | Possible, not expected |

| Impact | Meaning |
| --- | --- |
| Severe | Threatens the business |
| Major | Costs real money or a material number of clients |
| Moderate | Costs a client, a day, or a relationship |
| Minor | Absorbed in normal operation |

Four treatments: Avoid (don't do the thing) · Reduce (controls) · Transfer (insurance or contract) · Accept (watch it)

# PART 1 — What has already gone wrong

This section exists because it is the most honest part of the document.

| \# | Event | When | What it tells us |
| --- | --- | --- | --- |
| E1 | Speech engine transcribed "1827 Willow Bend" as "187 Willow Bend" | July 2026 | Transcription error is a live, recurring risk. Digit-by-digit readback was built in response and caught a wrong number on its first call. |
| E2 | Josh told a caller "there's no such thing as a house that fails, everything can be fixed or negotiated" | Aug 2026 | The AI will answer outside its scope unless explicitly prevented. Found in both the website demo and the phone script. |
| E3 | A ruling reached the phone agent and not the website agent | Aug 2026 | Two brains. An instruction that lands in one is not in force. |
| E4 | Four separate AI specialists produced fabricated content — invented statistics, invented workflow rules marked "live," invented client names | Jul–Aug 2026 | Small models with no working retrieval generate plausible answers. Root cause was infrastructure, not judgment. |
| E5 | Review gating was specified as a product feature | Jul 2026 | A compliance breach can be designed in with good intentions. Caught in spec, corrected before build. |
| E6 | Income figures published on the live website | Aug 2026 | Marketing drift toward earnings claims is persistent and recurs unless checked. |
| E7 | Spanish enablement measurably degraded address accuracy | Aug 2026 | A feature can create a defect in an unrelated function. |

Six of these seven were caught internally. That is the single most encouraging fact in this document — and the reason the controls below are worth writing down rather than trusting to memory.

# PART 2 — The Register

## 🔴 Tier 1 — Severe

### R1 · TCPA violation from a customer-supplied contact list

Likelihood: Medium · Impact: Severe

We send emails and SMS messages on customers' behalf to the lists they upload. Damages run $500–$1,500 per message. One customer uploading a purchased list of 5,000 contacts creates $2.5M–$7.5M in theoretical exposure.

| Controls | Gaps |
| --- | --- |
| Contractual warranty and indemnity | ⚠️ Indemnity is only as good as a one-man shop's ability to pay |
| Separate dated attestation at newsletter purchase | ⚠️ Attestation not yet built |
| We refuse purchased/scraped lists | ⚠️ No technical detection of a purchased list |
| Unsubscribe, bounce, and STOP handling |  |

Treatment: Reduce \+ Transfer. Build the attestation before the first newsletter sale. Confirm TCPA is not excluded from E\&O — if it is, schedule it.

### R2 · Data breach

Likelihood: Low–Medium · Impact: Severe

At 500 clients, we hold 400,000–800,000 recorded calls per year, plus names, phone numbers, email addresses, and property addresses of members of the public.

| Controls | Gaps |
| --- | --- |
| No card data held | ⚠️ No documented security controls |
| No health or financial account data | ⚠️ No incident response plan |
| Defined retention period | ⚠️ No breach notification procedure |
| Data not sold or cross-shared | ⚠️ Access controls not documented |

Treatment: Reduce \+ Transfer. Cyber cover, and the controls documented — underwriters price on them.

### R3 · 🔴 Key person dependency

Likelihood: Medium · Impact: Severe

Ken holds the industry credibility, the strategy, and the client relationships. Dil holds the technical operation. Neither is documented to the point where someone else could step in.

This is a real risk, not a formality. Ken closed a previous business for health reasons.

| Controls | Gaps |
| --- | --- |
| Written strategy documents | ⚠️ No documented succession |
| Decisions log | ⚠️ Systems knowledge is in Dil's head and Claude Code's context |
| Beth as co-owner | ⚠️ No key person insurance |
|  | ⚠️ Recorded material is the transferable asset, and most of it isn't recorded yet |

Treatment: Reduce. Record what Ken does the first time he does it. Document the technical architecture to the point a competent developer could take it over. Consider key person cover.

### R4 · Platform or vendor dependency failure

Likelihood: Medium · Impact: Severe

The service depends on a telecom carrier, a speech engine, AI model providers, a CRM platform, a payment processor, and cloud hosting. Any one of them can change terms, raise prices, or fail.

| Controls | Gaps |
| --- | --- |
| Corporate automation built in our own code, not the CRM | ⚠️ Contact data still lives in a third-party CRM |
| Speech engine already swapped once | ⚠️ No documented exit path from any vendor |
|  | ⚠️ No cost modelling if a vendor doubles pricing |

Treatment: Reduce \+ Accept. Know the exit path for each. Accept that some concentration is unavoidable at this size.

## 🟠 Tier 2 — Major

### R5 · Josh error at scale

Likelihood: High · Impact: Moderate per event, Major cumulatively

Wrong address, wrong price, wrong slot. E1 confirms it happens. At 500 clients and half a million calls, a 0.1% error rate is 500–800 errors a year.

Controls: digit-by-digit readback · pricing from customer rules · contractual verification duty · recordings and transcripts for dispute resolution

Gaps: ⚠️ no measured error rate · no systematic error monitoring · no defined correction procedure

Treatment: Reduce. Measure the error rate before launch and track it. Without a baseline, there's no way to know if it's getting worse.

### R6 · Service outage

Likelihood: Medium · Impact: Major

Every customer's phone goes unanswered simultaneously.

Controls: none documented

Gaps: 🔴 failover behaviour undefined · no status page · no notification procedure · no SLA · no answer to the question a prospect asks before signing

Treatment: Reduce. This is the most overdue item in the plan. Open since 6 August.

### R7 · AI acts outside its scope

Likelihood: Medium · Impact: Major

E2 is the proof. Josh gave advice about a house nobody had inspected, in the inspector's name. E3 shows a fix can land in one agent and not the other.

Controls: explicit scope rules · disclosure on request · automated drift check

Gaps: ⚠️ the drift check had been failing · rules do not survive translation (the Spanish agent used the banned word and dodged the AI question) · no periodic transcript review

Treatment: Reduce. Rules verified in both agents and every language, and a sample of live transcripts read weekly by a human.

### R8 · Compliance drift in marketing

Likelihood: High · Impact: Major

E5 and E6 both happened. Income figures reached the live site. Review gating was written into a spec as a feature.

Controls: copy gate · standing rules · sourcing convention · no-earnings-claims rule

Gaps: ⚠️ gate has been bypassed under time pressure · no pre-publication checklist · no periodic audit of live pages

Treatment: Reduce. A short pre-publication checklist, and a quarterly sweep of the live site.

### R9 · Delivery capacity

Likelihood: High · Impact: Major

White Glove setup is manual. At 500 clients that's 500 hand-built configurations plus ongoing accelerant delivery.

Controls: onboarding capacity is a stated constraint on the offer

Gaps: ⚠️ capacity number not established · snapshot contents unverified · accelerant cadence commitments not yet set · no per-client delivery time measurement

Treatment: Reduce. The cadence numbers in the agreement must be ones the team can meet on every client. A missed contractual scope is worse than no scope.

### R10 · Churn

Likelihood: High · Impact: Major

500 net is not 500 gross. At 10% annual churn, holding 500 takes \~650 acquisitions. At 30%, 900 or more — a 40% swing in total marketing cost.

Controls: Retention Engine · Business Center · James on the dashboard

Gaps: ⚠️ no churn measurement · no exit interview · no early-warning signal

Treatment: Reduce. Instrument it from client one, not from client fifty.

## 🟡 Tier 3 — Moderate

| \# | Risk | Note |
| --- | --- | --- |
| R11 | Double-booking | Contractually addressed. No technical prevention if a customer books outside the system. |
| R12 | Call recording consent | Josh announces on every call — a strong control. ⚠️ Announcement wording not legally reviewed. |
| R13 | Content published in a customer's name | Newsletters, review responses, microsites. Approval by exception. ⚠️ No pre-send review of anything naming a third party. |
| R14 | Standards of Practice — Home Pro Network | Advertising structure, disclaimers, customer responsibility stated. ⚠️ Attorney has not yet confirmed the structure holds. |
| R15 | Porting failure | Contract says service doesn't begin until the port completes. ⚠️ No procedure for a rejected port. |
| R16 | Stale context in the agent team | E4. Memory search now working, documents committed. ⚠️ Instructions still need updating when the log changes. |
| R17 | Spanish accuracy degradation | E7. Disclosed in the agreement, English default. ⚠️ Address accuracy not re-tested since enablement. |
| R18 | Pricing and unit economics | ⚠️ Not yet established. Cannot assess margin risk until Sterling's numbers exist. |

# PART 3 — 🔴 What has no control at all

The honest list. Everything here is currently uncontrolled.

| \# | Gap | Consequence |
| --- | --- | --- |
| 1 | Outage failover undefined | No answer for prospects, no answer for clients, no clause in the contract |
| 2 | No incident response plan | A breach or outage would be improvised |
| 3 | No measured Josh error rate | Cannot tell if quality is improving or degrading |
| 4 | TCPA attestation not built | The strongest control against the largest exposure doesn't exist yet |
| 5 | No security controls documented | Affects the cyber premium and the breach response |
| 6 | No succession documentation | Neither Ken nor Dil is replaceable today |
| 7 | Accelerant cadence not set | About to become contractual commitments |
| 8 | No insurance in force | Every transfer treatment above is theoretical |

Items 1, 4 and 8 are the ones I'd close before the first paying client.

# PART 4 — Treatment Summary

| Approach | Applied to |
| --- | --- |
| Avoid | No cold email or SMS · no review gating · no after-hours-only trial · no purchased lists · no earnings claims |
| Reduce | Digit readback · AI scope rules · recording announcement · approval by exception · copy gate · decisions log · Retention Engine |
| Transfer | Tech E\&O · cyber · media liability · contractual liability cap · customer indemnities · arbitration and class waiver |
| Accept | Some vendor concentration · some AI error rate · market conditions |

# PART 5 — Ownership and Review

| Risk area | Owner |
| --- | --- |
| Product and AI behaviour | Dil |
| Compliance and marketing claims | Ken, with the copy gate |
| Delivery capacity and quality | Beth |
| Financial and pricing | Ken / Sterling |
| Insurance and contracts | Ken |

Review cadence: monthly for Tier 1 and 2 · quarterly for the full register · immediately on any Tier 1 event

A risk is added whenever something goes wrong that isn't already on the list. Part 1 is how this document stays honest.

# PART 6 — Procedures Required

A risk plan without procedures is a list of worries. These are the runbooks that make the controls real, in order of urgency.

## Before the first paying client

| \# | Procedure | Closes |
| --- | --- | --- |
| P1 | Outage response — what happens to calls, who is notified, how, and how fast | R6, Gap 1 |
| P2 | Josh error correction — customer reports a wrong address, price or booking. Who fixes it, in what time, what the customer is told | R5, Gap 3 |
| P3 | New client onboarding — the White Glove checklist, including the port, the calendar cutover, and go-live verification | R9, R15 |
| P4 | Pre-publication check — the short list every piece of public copy passes before it ships | R8 |
| P5 | Incident response — breach, data loss, or a security event | R2, Gap 2 |

## Within the first quarter

| \# | Procedure | Closes |
| --- | --- | --- |
| P6 | Quality monitoring — sampling live transcripts, measuring the error rate, tracking it | R5, R7 |
| P7 | Complaint and dispute handling — including anything involving money or a live client | R13 |
| P8 | Change control for AI instructions — a rule reaches every agent and every language, and is verified | R7, R16, E3 |
| P9 | Churn monitoring and exit interview | R10 |
| P10 | Accelerant delivery checklists — one per accelerant, matching the contractual scope | R9 |

## Before scale

| \# | Procedure | Closes |
| --- | --- | --- |
| P11 | Vendor review — annual assessment of each dependency and its exit path | R4 |
| P12 | Succession and documentation — architecture, credentials, and continuity | R3 |
| P13 | Quarterly compliance audit — live site, agent knowledge, contract alignment | R8, R14 |

## What I'd do first

P1, P2 and P4 — and P1 unblocks the contract, the sales conversation and the insurance submission at the same time.

Say which one you want written and I'll draft it. They're short documents, and the point is that somebody can follow them at 9 pm without calling you.